## 1b) Project Portfolio
PROJECT PORTFOLIO — AWAITING SIGN OFF
Project ID | Project / Programme | Business Area | Strategic Priority (1=Quick ROI · 2=Risk/Reg · 3=CX · 4=Long ROI) | Comments
P001 | National Marketing Campaign (Billboards & Bus Shelters) | Marketing | 4
P002 | Customer Loyalty Programme | Customer | 3
P003 | Warehouse Expansion Programme | Warehouse | 4 | Costly project with a long timeline, 24 month project
P004 | Data Protection Process Improvements | Audit | 2
P005 | CRM System | Customer | 3 | Costly project, requires integrations with web and app
P006 | Email Receipts | Customer | 1
P007 | Social Media Management Tool | Customer | 1
P008 | Finance Software Upgrade | Finance | 4
P009 | Warehouse AI System | Warehouse | 4
P010 | Till System Upgrade | Stores | 4
PRIORITY KEY | 1 — Quick ROI | 2 — Risk / Reg | 3 — Customer Experience | 4 — Long ROI

## 2) Kanban Board
KANBAN BOARD — APP REFRESH PROJECT
TO DO | IN PROGRESS | DONE | NEXT SPRINT | FUTURE WORK
Demo software in place
CRM fields created
Customer account creation - ability to save favourite products
Product numbers created in app
Payment (card) connected to finance system
Payment facility (card) implemented in app
Payment facility (paypal) implemented and connected to finance system
Extra product lines added to app
Store location software updated
Navigate any store using the app
BBC News live feed built into app
Social media feeds updated in app
Email collector for newsletter feed updated
Finance reporting feed developed
Finance reporting feed tested
QR code for product offers
App design complete UX
App design complete UI
App design A/B testing(Strike Through - Not Aligned to Project)
Gaming built into app
App support process documented
App backup process documented (Disaster recovery)
App backup process tested (Disaster recovery)
App information security - features identified
App information security - features built
Sync with website in place

## 3) Risk Log
RISK LOG
Risk ID | Date Raised | Description (Cause & Effect - Clearly describe what the risk is and what the impact is) | Impact Rating (Enter 1-5) | Likelihood Rating (Enter 1-5) | Risk Score (Impact x Likelihood) | Action & Owner (What needs to happen to mitigate this risk or is it acceptable to do nothing at this stage?) | Target Action Completion Date (When will actions be completed by?) | Risk Owner (Who is responsible for mitigating this risk?) | Any Additional Comments / Any Escalation Required?
R001 | 2025-05-19 | Developers Lack Payment Tool Licences | 5 | 4 | 20 | Escalate to procurement to expedite licence purchase. Owner: Project Manager | 2025-05-26 | Project Manager | Escalate to leadership if licence delay exceeds 1 week.
R002 | 2025-05-19 | Information security features are incomplete | 5 | 4 | 20 | Prioritise security feature development in next sprint. Assign security consultant if needed. Owner: Project Manager | 2025-06-02 | Project Manager | Audit visit scheduled in 2 weeks — must be complete by then.
R003 | 2025-05-19 | UX/UI team overallocated to Website project | 4 | 3 | 12 | Re-negotiate resource share with Website PM to rebalance UX team. Owner: Project Manager | 2025-05-26 | Project Manager | Communicate prioritisation plan to Scrum Master and stakeholders.

## 4) Issue Log
ISSUE LOG
Risk ID | Date Raised | Description (Cause & Effect - Clearly describe what the issue is and what it is impacting - time, budget or quality) | Impact Rating (Enter 1-5) | Issue RAG | Action & Owner (What needs to happen to resolve this issue?) | Target Action Completion Date (When will actions be completed by?) | Issue Owner (Who is responsible for resolving this issue?) | Any Additional Comments / Any Escalation Required?
I001 - Missing Developer Licences | 2025-05-19 | Two developers are currently blocked due to missing software licences. Effect: Delayed progress on payment features, affecting Sprint 2 output. | 4 | 4 | PM to escalate with procurement and secure licences within 5 days. Owner: Project Manager | 2025-05-20 | Project Manager | Escalate to leadership if no resolution by end of Sprint 2.
I002 - Test Lead on Leave | 2025-05-19 | Test Lead is on annual leave for Sprint 3. Effect: Reduced testing capacity may delay quality assurance for upcoming deliverables. | 3 | 3 | Reassign QA responsibilities to senior dev or rotate coverage from other teams. Owner: Scrum Master | 2025-05-17 | Scrum Master | ’ll support the Scrum Master in adjusting plans — whether that means shifting tasks, changing priorities, or postponing lower-risk testing to Sprint 4.
I003 - 3rd Party Support Vendor SLA Degradation | 2025-05-19 | 3rd party app support vendor acquired. Effect: Service level agreements are no longer being consistently met, risking resolution delays. | 4 | 4 | Contact vendor leadership, review SLAs, and draft contingency support plan. Owner: Project Manager | 2025-05-22 | Project Manager | Escalation to Chief of Staff may be required if vendor continues to breach SLA.

## 5) Sprint 1 - Planned vs Actual
SPRINT 1 — PLANNED vs ACTUAL STORY POINTS
Metric | Dev 1 | Dev 2 | Dev 3 | Dev 4 | Tester | Total
Planned | 10 | 10 | 8 | 12 | 10 | 50
Actual | 5 | 10 | 8 | 20 | 11 | 54
Variance (Actual − Planned) | -5 | 0 | 0 | 8 | 1

## Risk Management Matrix
RISK MANAGEMENT MATRIX
IMPACT
|  | 1 - Very Low | 2 - Low | 3 - Medium | 4 - High | 5 - Very High
LIKELIHOOD | 5 - Very High | 5 | 10 | 15 | 20 | 25
| 4 - High | 4 | 8 | 12 | 16 | R001, R002
| 3 - Medium | 3 | 6 | 9 | R003 | 15
| 2 - Low | 2 | 4 | 6 | 8 | 10
| 1 - Very Low | 1 | 2 | 3 | 4 | 5
SCORE LEGEND | Low (1–6) | Medium (7–14) | High (15–25)