## 1b) Gymnasium Team Plan Templat
Project Plan Template
| KEY: |  | COMPLETE | Task/Milestone COMPLETE
|  |  | LATE | Task/Milestone LATE
|  |  | AT RISK | Task/Milestone AT RISK
|  |  | ON TRACK | Task/Milestone ON TRACK
CURRENT YEAR
| Q3 | [11 empty] | Q4 | [11 empty] | Q1 | [11 empty] | Q2 | [11 empty] | Q3
Key Milestone / Tasks | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 1 |  |  |  | Month 2 |  |  |  | Month 3
| Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
Business Case Signed Off
Receive Final Team Requirements (UK/China)
Design Adjustments for New Events
Finalise Layouts & Measurements
Order Team-Specific Equipment
Confirm Delivery & Suppliers
Install Team Area Equipment
Create Interactive Virtual Tour
Conduct Internal Walkthrough
Country Officials Virtual/In-Person Tours
Final Adjustments After Feedback
Snagging | bar: Month 1 Week 4; Month 2 Week 3 to Month 3 Week 4

## 3) Risk Log
RISK LOG
Risk ID | Date Raised | Description (Cause & Effect - Clearly describe what the risk is and what the impact is) | Impact Rating (Enter 1-5) | Likelihood Rating (Enter 1-5) | Risk Score (Impact x Likelihood) | Action & Owner (What needs to happen to mitigate this risk or is it acceptable to do nothing at this stage?) | Target Action Completion Date (When will actions be completed by?) | Risk Owner (Who is responsible for mitigating this risk?) | Any Additional Comments / Any Escalation Required?
R001 |  | Rooftop terrace safety certification deadline missed (HotelO24). This may result in legal action and delay project launch. | 5 | 4 | 20 | Escalate to legal and surveyor teams; assign expedited work order. Owner: Project Manager | End of Month 6 | Project Manager | High-profile legal risk; report at next Board meeting.
R002 |  | Virtual tour for Gymnasium newly requested by IOC Committee. Not scoped or budgeted, may delay readiness for country teams. | 4 | 3 | 12 | Scope tour, assign tech team lead, request additional funding. Owner: Tech Lead | Month 1, Q1 | Tech Lead | Escalate to Change Control Board for funding support.
R003 |  | Site Manager resignation (HotelO24). Loss of local knowledge and leadership could disrupt build schedule. | 4 | 5 | 20 | Source urgent contractor via HR or agency; assess budget impact. Owner: Operations Manager | Within 2 weeks | Operations Manager | Consider interim site leadership if recruitment delayed.
R004 |  | IOC legal agreement on hotel post-use still pending. May delay post-Games operational planning and stakeholder decisions. | 3 | 4 | 12 | Chase legal team and escalate through IOC channels. Owner: Project Manager | Month 7 | Project Manager | Escalate at next IOC status review.
R005 |  | Marketing materials for HotelO24 depend on IOC approval. Delay could impact pre-launch promotion. | 3 | 3 | 9 | Coordinate with IOC Comms Team. Owner: Hotel Manager | Month 8 | Hotel Manager | Monitor in monthly board reviews.
R006 |  | Late team layout requirements from UK/China. May delay equipment orders and room configuration. | 4 | 4 | 16 | Chase outstanding teams via Gym Committee. Owner: Gym Committee Member | Month 6 | Gym Committee Member | Track progress weekly; escalate delays.
R007 |  | Japanese tree import delay for gymnasium exterior. May impact landscaping and sponsor expectations. | 3 | 4 | 12 | Source alternative trees locally; inform sponsor. Owner: Operations Manager | Month 6 | Operations Manager | Flag in upcoming sponsor review.
R008 |  | Brexit-related import delays on gym equipment. May impact testing and readiness for Games. | 4 | 3 | 12 | Assess alternate suppliers (e.g. Australia). Owner: Tech Lead | Month 9 | Tech Lead | Update delivery tracker weekly.

## 4) Issue Log
ISSUE LOG
Risk ID | Date Raised | Description (Cause & Effect - Clearly describe what the issue is and what it is impacting - time, budget or quality) | Impact Rating (Enter 1-5) | Issue RAG (Auto: mirrors Impact) | Action & Owner (What needs to happen to resolve this issue?) | Target Action Completion Date (When will actions be completed by?) | Issue Owner (Who is responsible for resolving this issue?) | Any Additional Comments / Any Escalation Required?
I001 |  | Rooftop terrace safety certificate deadline missed. Launch may be delayed and hotel chain may pursue legal action. | 5 | 5 | Escalate to legal/surveyor team. Prioritise terrace safety confirmation. Owner: Project Manager | Month 6 | Project Manager | Report immediately to board; legal risk.
I002 |  | Site Manager resigned unexpectedly. On-site coordination and timeline may suffer if not replaced urgently. | 4 | 4 | Recruit interim contractor. Confirm availability. Owner: Operations Manager | 2 weeks from date raised | Operations Manager | Escalate resourcing to HR.
I003 |  | Marketing materials for HotelO24 not yet approved by IOC. Hotel promotion campaign is blocked. | 3 | 3 | Submit material draft to IOC Comms team. Request fast-track review. Owner: Hotel Manager | Month 8 | Hotel Manager | Raise during next IOC call.
I004 |  | Internal Fit-Out delayed due to incomplete materials procurement for specific fixtures. | 3 | 3 | Review procurement log. Expedite missing items. Owner: Project Manager | Month 9 | Project Manager | Coordinate with logistics and procurement team.
I005 |  | Hotel staff induction cannot proceed as planned due to incomplete site access. | 4 | 4 | Coordinate access with build contractor. Confirm readiness for staff tours. Owner: Hotel Manager | Month 8 | Hotel Manager | Include in pre-launch checklist.
I006 |  | Post-Games conversion costs for hotel significantly underestimated. €1.5m variance identified. | 4 | 4 | Update forecast. Present cost deviation to stakeholders. Owner: Project Manager | Month 10 | Project Manager | Add to next governance meeting agenda.
I007 |  | Virtual tour was not scoped or budgeted. IOC requirement now urgent. | 4 | 4 | Engage tech team and request funding. Owner: Tech Lead | Month 1, Q1 | Tech Lead | Submit to Change Control Board.
I008 |  | Equipment delivery facing delays due to Brexit-related customs challenges. | 4 | 4 | Confirm shipping schedule; explore alternative suppliers. Owner: Operations Lead | Month 9 | Operations Lead | Track delays weekly.
I009 |  | Requirements from UK/China gym teams still not received. Delaying design completion. | 4 | 4 | Follow up with Gym Committee and NGBs. Owner: Gym Committee Member | Month 6 | Gym Committee Member | Escalate to project sponsor if unresolved.
I010 |  | Japanese tree imports delayed due to shipping. Affects gym exterior landscaping. | 3 | 3 | Source local alternatives and update stakeholders. Owner: Operations Manager | Month 6 | Operations Manager | Sponsor visibility required.
I011 |  | Design adjustments for new events not yet finalised. May impact gym configuration and flow. | 3 | 3 | Work with design lead to lock event layout. Owner: Design Lead | Month 7 | Design Lead | Align with Gym Committee schedule.
I012 |  | Paralympics Readiness Not Yet Confirmed | 4 | 4 | Coordinate monthly with Paralympics Office. Owner: Project Manager | Month 9 | Project Manager | Document progress in monthly IOC report.

## 9) Project Manager Actions Log
ACTIONS LOG
Action ID | Date Raised | Action Description (Cause & Effect - Clearly describe what the risk is and what the impact is) | Priority of Action High - Requires Urgent Attention Medium - Requires Attention within the next 2 weeks Low - Requires Attention at a much later date | Action Owner | Any Additional Comments
A001 |  | Replace Site Manager | High | Operations Manager | Critical to maintaining project momentum
A002 |  | Certify Rooftop Terrace | High | Building Surveyor | Must comply with hotel chain’s legal requirements, with completion required by Month 6 to prevent delays to readiness activities scheduled for Months 8–9.
A003 |  | Finalise Marketing Content for IOC | Medium | Hotel Manager | Send for IOC sign-off by end of Month 7
A004 |  | Approve Extra Funding for Conversion | High | Programme Sponsor | This issue needs to be reviewed and decided by senior leadership at a Steering Committee meeting, as it involves a major funding decision that cannot be approved at the project level.
A005 |  | Confirm Induction Visit Planning | Medium | Project Manager | Induction cannot happen until the terrace and internal fit-out are complete
A006 |  | Gather Missing Team Inputs | High | Gym Project Manager | If UK and China team inputs aren’t received by Month 6, the Project Manager should escalate to their National Olympic Committee reps for resolution.
A007 |  | Lock Layout for New Events | High | Design Lead | PM should discuss the extension of the Design Lead’s contract in the next governance call.
A008 |  | Order Accessibility Equipment | Medium | Operations Manager | Align with the Month 8–9 installation timeline to ensure timely delivery and prevent delays to final testing and accessibility compliance.
A009 |  | Scope and Plan Virtual Tour | Medium | Tech Lead | Budget and supplier quotes are needed by Month 9 to allow sufficient time for development and testing ahead of pre-Games team orientation.
A010 |  | Resolve Gym Equipment Shipping Delay | High | Logistics Coordinator | Explore alternative shipping options or rerouting to prevent delays to equipment installation and ensure the gym remains on track for final readiness.

## Risk Management Matrix
RISK MANAGEMENT MATRIX
IMPACT
|  | 1 - Very Low | 2 - Low | 3 - Medium | 4 - High | 5 - Very High
LIKELIHOOD | 5 - Very High | 5 | 10 | 15 | R003 | 25
| 4 - High | 4 | 8 | R004, R007 | R006 | R001
| 3 - Medium | 3 | 6 | R005 | R002, R008 | 15
| 2 - Low | 2 | 4 | 6 | 8 | 10
| 1 - Very Low | 1 | 2 | 3 | 4 | 5
SCORE LEGEND | Low (1–6) | Medium (7–14) | High (15–25)
SCORE LEGEND | Low Risk (1–6) | Medium Risk (7–14) | High Risk (15–25)